## Arkusz1
Baba Jaga Patrzy |  | Month | October |  |  |  | November |  |  |  | December |  |  |  | January
|  | Week | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV
Task name | Task owners
Project PoC | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: October I to October II
Create GIT Repository | Paweł Tymoczko | bar: October II
Design PCB for Game Module | Mariusz Furtek, Paweł Kierzek | bar: January III
Describe Game rules | Mariusz Furtek | bar: October III
Choose hardware elements & collect datasheets | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: October II to October III
Design software architecture for control module | Mariusz Furtek, Paweł Kierzek | bar: December I to December IV
Design software architecture for game module | Paweł Tymoczko | bar: November II to January III
Create Prototype hardware set for game module on breadboard | Paweł Tymoczko | bar: November I to December I
Create Prototype hardware set for control module on breadboard | Mariusz Furtek, Paweł Kierzek | bar: November II to November IV
Integrate software modules | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: December IV to January III
Integrate prototype electronic systems | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: December IV to January III
Movement detection - PoC & write simple program to test functionality | Paweł Tymoczko | bar: November II
Learn Altiume | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: January II to January III
Configure IDE & programming setup | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: October IV to November I
NucleoL432KC microcontroller onboarding | Paweł Tymoczko | bar: November I to November II
Implement EXTI for PIR signal PoC | Paweł Kierzek, Paweł Tymoczko | bar: November II to November III
Create basic algorithm for 2-side movement detection | Paweł Tymoczko | bar: November III to November IV
Control Module interface PoC | Mariusz Furtek, Paweł Kierzek | bar: November IV
STM32CubeIDE onboarding | Paweł Tymoczko | bar: November I to November II
Introduce common configuration interface for Game and Control modules via Bluetooth | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: December IV to January III
Implement bluetooth receiving mechanism using UART for Game module | Paweł Tymoczko | bar: December III to January I
Prepare set of messages to control Game logic | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: December III
Document messages types and definitions which controls flow of the game | Paweł Tymoczko | bar: December IV
Prepare block diagram for Game module | Paweł Tymoczko | bar: October III to October IV
Prepare block diagram for Control module | Mariusz Furtek, Paweł Kierzek | bar: October III to October IV
Create mobile app to substitute hardware based Control module | Mariusz Furtek, Paweł Kierzek | bar: January III
Add missed button functionality to Game module | Paweł Tymoczko | bar: January III
Prepare workspace in trello | Paweł Tymoczko | bar: October II
Create project's final report | Paweł Tymoczko
Update datasheets and cleen repository | Mariusz Furtek, Paweł Kierzek, Paweł Tymoczko | bar: January III